## Worksheet
Risk Identifier | Risk Description | Likelihood | Impact | Risk Score (L×I) | Mitigation Strategy | Owner | Review Date | Status
R-001 | Client data breach due to unsecured access points | High | Critical | 9 | Implement multi-factor authentication and network segmentation | IT Security Team | 2024-03-15 | Active
R-002 | Service outages due to vendor dependency | Medium | High | 6 | Establish alternative service providers and SLA monitoring | Operations Manager | 2024-04-01 | In Progress
R-003 | Regulatory non-compliance due to policy gaps | Low | High | 3 | Conduct quarterly compliance audits and update policies | Compliance Officer | 2024-05-10 | Planned
R-004 | Client churn due to poor service delivery | High | Medium | 6 | Improve customer feedback loop and service response time | Customer Success Lead | 2024-03-30 | Active
R-005 | Financial fraud via compromised payment gateways | High | Critical | 9 | Enhance transaction monitoring and real-time alerts | Fraud Prevention Unit | 2024-04-15 | Active