## Worksheet
Risk ID | Risk Description | Likelihood | Impact | Risk Rating | Assigned To | Mitigation Plan | Owner | Due Date | Status
R-001 | Failure of critical CRM system during peak usage | High | Critical | Severe | IT Operations Team | Implement redundant servers and load balancing. | DevOps Manager | 2024-05-30 | Active
R-002 | Data breach due to unpatched software vulnerabilities | Medium | High | <High | Security Team | Deploy automated patch management and conduct monthly vulnerability scans. | Chief Information Security Officer | 2024-06-15 | In Progress
R-003 | Poor customer data quality leading to miscommunication | Low | Medium | Moderate | Data Governance Team | Initiate data validation workflows and introduce quality checks in CRM entry forms. | Data Manager | 2024-07-10 | Planned
R-004 | System downtime due to third-party API failures | High | Critical | Severe | Integration Team | Develop fallback mechanisms and cache data during API outages. | Lead Integrations Engineer | 2024-05-10 | Active