## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact th> | Risk Score | Assigned To | Current Status | Mitigation Plan | Due Date
RISK-001 | System outage due to hardware failure | Operational | High | High | 9 | IT Department | Active | Install redundant servers and backup power systems. | 2024-06-30
RISK-002 | Data breach via phishing attack | Security | Medium | Critical | 7 | Cybersecurity Team | Monitoring | Implement multi-factor authentication and employee awareness training. | 2024-07-15
RISK-003 | Supplier delay in product delivery | Supply Chain | Low | Medium | 3 | Procurement Manager | Planned | Identify alternate suppliers and build buffer stock. | 2024-08-20
RISK-004 | Regulatory non-compliance | Compliance | High | High | 9 | Legal & Compliance Officer | Reviewing | Conduct internal audit, update policies, and train staff. | 2024-09-05