## Worksheet
Date | Risk Identified | Impact Level | Likelihood | Risk Score (Impact × Likelihood) | Owner | Mitigation Strategy | Status | Next Review Date
2024-04-01 | System downtime due to server failure | High | Medium | 6 | IT Operations Team | Implement redundant server setup and auto-failover protocol | Open | 2024-04-15
2024-04-02 | Data breach via unsecured API endpoint | Critical | High | 12 | Security Team | Restrict API access, enforce encryption, implement rate limiting | In Progress | 2024-04-10
2024-04-03 | Third-party vendor non-compliance | Medium | Low | 3 | Compliance Officer | Require SLA audit and compliance certification before engagement | Planned | 2024-04-25
2024-04-04 | Outage during peak load hours | High | Medium | 6 | DevOps Team | Scale application horizontally and schedule load testing | Open | 2024-04-20