## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Current Status | Owner | Mitigation Plan | Due Date | Last Reviewed
R-001 | Data breach due to outdated software | Cybersecurity | High | Critical | Active | Jane Smith | Patch all systems by end of Q3; implement multi-factor authentication. | 2024-09-30 | 2024-03-15
R-002 | Supply chain disruption from regional supplier issues | Operational | Medium | High | Monitoring | Alex Chen | Identify alternate suppliers; establish emergency procurement protocol. | 2024-11-15 | 2024-04-05
R-003 | Employee misconduct leading to reputational damage | Compliance | Low | High | Pending Review | Maria Garcia | Conduct employee training on ethics; revise code of conduct policy. | 2024-10-31 | 2024-05-10
R-004 | Regulatory changes impacting pricing model | Legal | Medium | Medium | Planned Action | David Kim | Establish regulatory watch group; update pricing compliance dashboard. | 2024-12-10 | 2024-06-01