## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Score | Owner | Mitigation Strategy | Status | Last Reviewed Date
R001 | System outage due to server failure | Operational Risk | High | High | 9 (9/10) | J. Smith | Implement redundant servers and backup procedures | Pending Action | 2024-03-15
R002 | Data breach via unsecured API access | Security Risk | Medium | High | 7 (7/10) | A. Johnson | Enforce API authentication and encryption standards | In Progress | 2024-03-10
R003 | Supply chain delay due to vendor issues | External Risk | Medium | Moderate | 5 (5/10) | M. Davis | Diversify vendor base and establish alternate suppliers | Active Monitoring | 2024-03-01
Total Risks Identified |  |  |  |  | 3 | Template Version 2.1 ¦ Purpose: Risk Management ¦ Template Type: CRM Tracker