## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact th> | Current Status | Owner | Mitigation Plan | Last Updated | Next Review Date
RISK-001 | Data breach due to unsecured APIs | Security | High | Critical | Active | Jane Smith | Implement API encryption and access controls | 2024-03-15 | 2024-06-15
RISK-002 | System outage during peak hours | Operational | Medium | High | Monitoring | John Doe | Deploy load balancing and auto-scaling infrastructure | 2024-03-10 | 2024-09-10
RISK-003 | Vendor contract expiration without renewal | Contractual | Low | Medium | Planned | Lisa Chen | Initiate renewal negotiations and evaluate alternatives | 2024-03-05 | 2024-12-05
RISK-004 | Compliance gap in data retention policies | Regulatory | High | Critical | Active | Mark Taylor | Update retention policy and conduct compliance audit | 2024-03-08 | 2024-11-08