## Worksheet
Date | Risk Identified | Risk Level | Potential Impact | Mitigation Strategy | Responsible Person | Status
2024-04-05 | Data Breach Due to Unsecured Endpoint | High | Loss of sensitive client data, regulatory fines | Implement endpoint encryption and access controls | J. Smith | Active - Monitoring
2024-04-05 | Third-party Vendor Delay | Moderate | Project timeline extension, cost overruns | Establish backup vendor and adjust scheduling | A. Lee | Pending Review
2024-04-06 | Network Outage During Peak Hours | High | Downtime affecting client services, reputational damage | Deploy redundant network path and perform load testing | M. Torres | Planned - Q2 Initiative
2024-04-07 | Inadequate Employee Training on Cyber Hygiene | Medium | Increased phishing susceptibility, internal security breach risk | Conduct quarterly training sessions and phishing simulations | S. Gupta | Upcoming - Scheduled for April 15