## Worksheet
Date | Risk Identified | Likelihood | Impact> | Risk Score (L×I) | Mitigation Action | Responsible Party | Due Date | Status
2024-04-01 | System outage due to hardware failure | High | Medium | 6 | Replace server every 3 years; implement backup protocol | J. Smith | 2024-04-15 | Pending
2024-04-01 | Data breach via phishing attack | Medium | High | 6 | Conduct quarterly phishing simulations and employee training | L. Davis | 2024-04-30 | In Progress
2024-04-01 | Third-party vendor non-compliance | Low | High | 3 | Mandatory audit and contract review every 6 months | M. Chen | 2024-05-15 | To Do
2024-04-01 | Network latency during peak hours | High | Low | 5 | Optimize routing and upgrade bandwidth in Q3 | T. Reed | 2024-07-31 | Pending