## Daily Risk Management Planner
Daily Risk Management Planner (Style: Daily)
Date | Activity/Task | Identified Risks | Risk Level (Low/Medium/High) | Impact Assessment | Probability Assessment th> | Mitigation Strategy | Status (Open/Resolved) th>
2024-04-05 | Project Kickoff Meeting | Delays in stakeholder alignment, poor communication channels | Medium | Moderate – affects timeline and scope | Medium – possible due to unclear roles | Schedule a pre-meeting briefing; assign clear responsibilities. | Open
2024-04-06 | Resource Allocation Review | Overcommitment of team members, availability gaps | High | High – could lead to burnout and reduced productivity | High – current workload exceeds capacity by 30% | Rebalance tasks; introduce temporary support resources. | Open
2024-04-07 | Vendor Onboarding Process | Vendor delay in deliverables, lack of SLAs | Medium | Moderate – impacts project timeline by 3–5 days | Medium – vendor history shows inconsistent delivery times | Define clear SLAs and include penalties for delays. | Open
2024-04-08 | Security Audit Preparation | Inadequate access controls, outdated software | High | Severe – potential data breach risk | High – system vulnerabilities detected in logs | Immediately patch systems and implement role-based access. | Open