## Worksheet
Date | Risk Identified | Risk Level (Low/Med/High/Critical) | Potential Impact | Likelihood | Owner / Responsible Party | Mitigation Strategy | Monitoring & Review Frequency | Status (Open/In Progress/Resolved) | Notes / Additional Details
2023-10-01 | Server downtime due to hardware failure | High | Loss of critical services and customer access | Medium | IT Operations Team | Implement redundant servers and automated failover protocols | Daily (after 8 PM) | Open | Initial assessment; no known workarounds yet.
2023-10-01 | Data breach via unpatched software | Critical | Loss of sensitive customer data and regulatory penalties | High | Security & Compliance Officer | Immediate patch deployment, firewall rule enforcement, and employee training | Every 4 hours (during peak) | In Progress | Two patches have been deployed; ongoing vulnerability scan.
2023-10-02 | Third-party vendor delay in delivery | Medium | Delays in project milestones and increased costs | Medium | Project Manager (PM-04) | Reallocate internal resources and negotiate revised timelines | Weekly review on Monday | Open | No alternative vendor identified yet.
2023-10-03 | Employee access to unauthorized systems | High | Exposure of internal data and potential fraud | Medium | HR & Security Team (Joint) | Implement role-based access controls and mandatory audit logs | Monthly audit with quarterly review | Open | New access policies drafted; awaiting approval.