## Worksheet
Date | Risk Identified | Risk Level | Likelihood | Impact | Mitigation Action | Responsible Employee | Status | Next Review Date
2023-10-05 | Data breach due to unsecured network access | High | Medium | High | Implement multi-factor authentication for all access points | Sarah Johnson | In Progress | 2023-10-15
2023-10-06 | Server downtime during peak hours | Medium | High | Medium | Schedule redundant server infrastructure and load balancing | Michael Chen | Planned | 2023-10-25
2023-10-07 | Insider threat from employee access to sensitive data | High | Low | High | Enforce strict data access controls and regular audits | Lisa Wong | Active | 2023-10-30
2023-10-08 | Third-party vendor security failure | Medium | Medium | High | Require vendor security compliance certifications and regular reviews | David Kim | Pending Approval | 2023-10-18