## Worksheet
Date | Risk Identified | Potential Impact | Likelihood | Risk Rating (High/Medium/Low) | Mitigation Strategy | Owner | Action Status | Review Date
2024-04-01 | Data breach due to outdated software | High financial and reputational damage | High | High | Implement software patching schedule and conduct quarterly audits | IT Security Manager | In Progress | 2024-04-15
2024-04-03 | Vendor dependency on single supplier | Medium to high operational disruption | Medium | Medium | Develop secondary vendor agreements and diversify supply chain | Procurement Director | Planned | 2024-05-01
2024-04-05 | Cyberattack from phishing campaign | High employee and system compromise | High | High | Conduct employee training and deploy advanced email filters | HR & Cybersecurity Lead | Pending Review | 2024-04-10
2024-04-08 | Regulatory non-compliance in data handling | High legal penalties and fines | Medium | High | Update compliance policy and conduct annual audit | Compliance Officer | Completed | 2024-04-08