## Worksheet
Date | Risk Identified | Likelihood | Impact th> | Risk Rating | Mitigation Plan | Owner | Status
2023-10-01 | Server downtime due to hardware failure | High | High | Severe | Replace critical servers every 3 years; implement redundant systems | Alex Johnson | Pending Action
2023-10-05 | Insufficient data encryption in transit | Medium | High | High | Migrate to end-to-end TLS 1.3 encryption; audit all endpoints | Sarah Lee | In Progress
2023-10-10 | Phishing attacks on employees | High | Medium | Moderate | Conduct bi-weekly phishing simulations and training sessions | Mike Chen | Completed
2023-10-15 | Third-party vendor data breach risk | Medium | High | High | Implement vendor security audits and SLAs with compliance checks | Lena Patel | To Review
2023-10-20 | Insufficient access controls in cloud environments | High | Medium | Moderate | Enforce principle of least privilege; audit role-based permissions monthly | Raj Singh | Planned Action