## Worksheet
Date | Risk Identified | Risk Level | Impact | Likelihood | Mitigation Plan | Responsible Party | Next Review Date
2024-04-05 | Cybersecurity breach due to outdated software | High | Critical | Medium | Patch all systems by end of week; conduct security audit. | IT Security Team | 2024-04-12
2024-04-05 | Supply chain delay due to vendor issues | Medium | Moderate | Low | Identify alternate suppliers; update procurement plan. | Procurement Manager | 2024-04-19
2024-04-05 | Data privacy violation during employee onboarding | High | Critical | High | Train staff on data handling protocols; implement access controls. | HR & Compliance Officer | 2024-04-15
2024-04-05 | Power outage affecting data center operations | Medium | High | Medium | Upgrade backup generators; test failover procedures weekly. | Facilities Manager | 2024-04-10
2024-04-05 | Regulatory change in compliance requirements | Low | Moderate | Medium | Review policy updates; schedule compliance training. | Legal & Compliance Team | 2024-04-26