## Worksheet
Date | Risk Identified | Impact Level | Probability | Mitigation Strategy | Responsible Party | Action Deadline | Status
2024-04-05 | Network outage due to hardware failure | High | Medium | Replace critical routers every 3 years; implement redundant connections | IT Operations Team | 2024-04-15 | In Progress
2024-04-06 | Data breach from unpatched software | High | High | Automate patch management; conduct quarterly vulnerability scans | Security Team | 2024-04-10 | Pending Review
2024-04-07 | Supply chain delay affecting delivery | Moderate | Medium | Diversify suppliers; maintain safety stock for critical items | Logistics Manager | 2024-04-12 | Planned
2024-04-08 | Employee access to sensitive data | Moderate | Medium | Enforce role-based access controls; conduct mandatory training | HR & Security Team | 2024-04-14 | Scheduled