## Worksheet
Date | Risk Identified | Potential Impact | Likelihood | Mitigation Strategy | Responsible Party | Status (Open/Closed) | Next Review Date
2024-04-01 | Server outage due to hardware failure | High - Business disruption and data loss | Medium | Implement redundant servers with automated failover | IT Operations Team | Open | 2024-04-15
2024-04-02 | Third-party vendor delay in delivery | Medium - Project timeline impact | Low to Medium | Identify backup suppliers and update procurement plan | Project Manager & Procurement Team | Open | 2024-04-10
2024-04-03 | Security breach via phishing attack | High - Data exposure and compliance risk | High | Enhance employee training and implement multi-factor authentication | Cybersecurity Team | Open | 2024-04-08
2024-04-05 | Unexpected regulatory change | High - Compliance penalties and operational adjustments | Medium | Establish a regulatory monitoring system and legal review process | Legal & Compliance Office | Open | 2024-04-18
2024-04-06 | Software update causing system instability | Medium - User experience degradation | Low | Roll back update and conduct thorough testing before next deployment | Development & QA Team | Closed | 2024-04-15