## Worksheet
Date | Risk Identifier | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Rating | Mitigation Strategy | Responsible Person | Due Date | Status
2023-10-05 | RISK-001 | Network downtime due to server failure | 4 | 5 | High | Implement redundant servers and automatic failover | IT Manager | 2023-10-10 | In Progress
2023-10-05 | RISK-002 | Data breach due to unauthorized access | 3 | 4 | Moderate | Enforce multi-factor authentication and regular audits | Security Officer | 2023-10-08 | Pending Review
2023-10-05 | RISK-003 | Project scope creep leading to delays | 5 | 4 | High | Establish strict change control process and weekly reviews | Project Lead | 2023-10-15 | Not Started
2023-10-05 | RISK-004 | Vendor performance failure | 3 | 3 | Moderate | Include performance SLAs in contracts and conduct bi-weekly reviews | Procurement Manager | 2023-10-12 | Planned