## Worksheet
Date | Time | Risk Identified | Potential Impact | Likelihood | Mitigation Strategy | Responsible Person | Status
2024-04-05 | 09:00 AM | Supplier delay in raw materials | Medium to High (production halt) | Medium | Identify backup suppliers and pre-order buffer stock | Sarah Chen | In Progress
2024-04-05 | 14:30 PM | Customer data breach risk | High (reputation & legal) | High | Enhance firewall and conduct staff training on phishing | James Lee | Planned
2024-04-06 | 10:15 AM | Power outage at office location | Medium (work interruption) | Low to Medium | Install UPS and backup generator plan | Maria Gonzales | Pending Approval
2024-04-07 | 16:00 PM | Key employee leaving unexpectedly Know-how loss | High (operational disruption) | Medium | Document processes and assign cross-training roles | David Patel | <Action Required