## Worksheet
Date | Team Member | Risk Identified | Impact Level | Likelihood | Risk Score (Impact × Likelihood) | Mitigation Action | Owner | Due Date | Status
2024-04-01 | Sarah Johnson | Server downtime during peak hours | High | Medium | 6 | Implement automated backup and load balancing | DevOps Team | 2024-04-15 | In Progress
2024-04-02 | Michael Chen | Data breach from outdated software | Critical | High | 12 | Patch all legacy systems and enforce access controls | Security Team | 2024-04-10 | Pending Review
2024-04-03 | Aisha Patel | Third-party vendor delay | Medium | Low | 3 | Identify alternative vendors and create contingency plan | Project Manager | 2024-04-18 | Not Started
2024-04-05 | David Kim | Employee error leading to data entry mistake | Low | Medium | 4 | Implement dual review process and training sessions | HR & Compliance | 2024-04-20 | Planned