## Worksheet
Risk Management – Finance Template (Advanced)
Risk ID | Risk Description | Asset Affected | Probability (1-5) | Impact (1-5) | Risk Score (P×I) | Risk Category | Owner | Status | Mitigation Strategy | Action Plan th> | Last Reviewed Date th>
RISK-001 | Market volatility affecting investment portfolios | Equity Funds, Fixed Income Portfolio | 4 | 5 | 20 | Market Risk | J. Smith | Active | Diversification, Hedging Instruments | Evaluate quarterly and adjust allocation. th> | 2024-03-15
RISK-002 | Regulatory changes impacting compliance costs | Compliance Department, Legal Team | 3 | 4 | 12 | Compliance Risk | L. Chen | Pending Review | Update policy documentation and training. th> | Schedule review with legal counsel by Q2 2024. th> | 2024-03-10
RISK-003 | Technology system failure leading to data loss | ERP System, Customer Database | 5 | 5 | 25 | Cyber/Operational Risk | M. Patel | Critical - High Priority th> | Backup systems, redundancy protocols. th> | Implement failover and disaster recovery by end of Q1 2024. th> | 2024-03-05