## Worksheet
Risk Identifier | Risk Description | Likelihood | Impact | Risk Score (L×I) | Mitigation Strategy | Responsible Party | Monitoring Frequency | Status
R-001 | Market volatility affecting revenue projections | Medium | High | 6 | Diversify investment portfolio and implement hedging instruments | Finance Team | Monthly | Active
R-002 | Regulatory changes impacting compliance costs | High | Medium | 9 | Conduct regulatory impact analysis and update policy framework | Legal & Compliance Team | Quarterly | Active
R-003 | Supply chain disruption due to geopolitical issues | High | High | 12 | Establish alternative suppliers and develop contingency plans | Operations Team | Bi-annual | On Review
R-004 | Technological obsolescence in core systems | Medium | High | 6 | Initiate system modernization project with phased rollout | IT Department | Annual | Planned
R-005 | Key personnel departure affecting project delivery | Medium | High | 6 | Implement knowledge transfer programs and cross-train team members | HR & Project Management Team | Quarterly | Active