## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Risk Level | Mitigation Strategy | Status
Risk Identification Workshop | 2024-03-15 | 2024-03-17 | 3 | Project Manager | Medium | Conduct stakeholder interviews and use risk matrix. | Completed
Threat Assessment & Analysis | 2024-03-18 | 2024-03-25 | 8 | Security Analyst | High | Apply vulnerability scanning and historical data review. | In Progress
Risk Prioritization & Scoring | 2024-03-26 | 2024-03-31 | 6 | Risk Officer | High | Use RACI matrix and probability-impact scoring. | Planned
Mitigation Planning & Action Items | 2024-04-01 | 2024-04-10 | 10 | Project Team | Medium | Implement controls and assign owners. | Scheduled
Monitoring & Review Cycle | 2024-04-11 | 2024-06-30 | 91 | Risk Manager | Low | Monthly reviews with updated risk register. | Ongoing