## Worksheet
Date | Task | Responsible | Risk Identified | Impact Level | Mitigation Strategy | Status
2023-10-01 | System Downtime Risk Assessment | John Smith | Server failure during peak load | High | Implement redundancy and load balancing | In Progress
2023-10-03 | Data Breach Prevention Review | Lisa Chen | Unauthorized access to customer data | Critical | Enforce multi-factor authentication and regular audits | Planned
2023-10-05 | Third-Party Vendor Risk Audit | Mike Rodriguez | Vendor non-compliance with data policies | Medium | Require annual security certifications and SLAs | Completed
2023-10-07 | Incident Response Plan Update | Sarah Kim | Delayed incident escalation process | High | Define clear escalation paths and response timelines | Pending Review
2023-10-10 | Risk Communication Strategy | David Lee | Stakeholders unaware of risk exposure | Medium | Monthly risk briefings and dashboard updates | Scheduled