## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Responsible Party | Risk Level | Mitigation Strategy | Status | Dependencies
RMS-001 | Identify Key Risks | 2024-03-15 | 2024-03-25 | 11 | Risk Management Team | High | Conduct stakeholder interviews and risk workshops | In Progress | None
RMS-002 | Assess Risk Impact and Likelihood | 2024-03-26 | 2024-04-10 | 15 | Risk Analysts | Medium | Apply risk matrix scoring model (Likelihood × Impact) | Planned | RMS-001
RMS-003 | Develop Risk Mitigation Plans | 2024-04-11 | 2024-05-05 | 25 | Project Manager & Risk Team | High | Implement controls, assign owners, and define response actions | Planned | RMS-002
RMS-004 | Monitor and Review Risks Weekly | 2024-05-06 | 2024-12-31 | 249 | Risk Management Office | Low to Medium | Conduct weekly risk review meetings and update risk register | Ongoing | RMS-003
RMS-005 | Document and Report Risks to Stakeholders | 2024-12-31 | 2025-01-15 | 46 | Executive Sponsor | High | Prepare and present comprehensive risk report to senior management | Planned | RMS-004