## Worksheet
Task | Start Date | End Date | Duration | Responsible Employee | Status | Risk Level
Risk Assessment Planning | 2024-03-01 | 2024-03-15 | 15 days | Sarah Johnson | Completed | Low
Identify Key Risks | 2024-03-16 | 2024-04-05 | 21 days | Michael Chen | In Progress | Medium
Risk Mitigation Strategy Development | 2024-04-06 | 2024-05-10 | 35 days | Emily Rodriguez | Planned | High
Risk Monitoring & Review Meetings | 2024-05-11 | 2024-08-31 | 123 days | Team Lead (All) | Scheduled | Medium
Final Risk Report Submission | 2024-09-01 | 2024-09-15 | 15 days | Sarah Johnson | Planned | Low