## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Risk Level | Status
Risk Assessment & Identification | 2024-03-01 | 2024-03-15 | 15 | Risk Management Team | High | In Progress
Threat Modeling Workshop | 2024-03-16 | 2024-03-25 | 10 | Security Analysts | Medium | Planned
Risk Mitigation Strategy Development | 2024-03-26 | 2024-04-10 | 15 | Strategy Office | High | Scheduled
Implementation of Controls | 2024-04-11 | 2024-05-31 | 60 | IT Operations | Medium | Not Started
Monitoring & Review Cycle | 2024-06-01 | 2024-06-30 | 30 | Compliance Officer | Low | Planned