## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Risk Level | Status
Risk Assessment Planning | 2024-01-01 | 2024-01-15 | 15 | Jane Smith | Medium | In Progress
Identify Critical Risks | 2024-01-16 | 2024-01-31 | 16 | Mark Johnson | High | Pending Review
Risk Mitigation Strategy Development | 2024-02-01 | 2024-02-15 | 15 | Lisa Chen | Medium | Planned
Stakeholder Risk Communication Plan | 2024-02-16 | 2024-03-01 | 16 | Alex Rivera | Low | Not Started
Monitor & Review Risks Monthly | 2024-03-01 | 2024-12-31 | 365 | Team Lead | Low | Ongoing