## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Risk Identification | 2024-03-01 | 2024-03-15 | 15 | Risk Officer | Completed
Risk Assessment | 2024-03-16 | 2024-04-10 | 35 | Risk Analysts | In Progress
Mitigation Planning | 2024-04-11 | 2024-05-31 | 61 | Project Manager | Planned
Risk Review & Validation | 2024-06-01 | 2024-06-15 | 15 | Risk Committee | Not Started
Continuous Monitoring | 2024-06-16 | 2025-12-31 | 378 | Operations Team | Not Started