## Worksheet
Week | Risk Identification | Risk Assessment | Mitigation Plan | Responsible Party | Timeline (Weeks) | Status
1 | Identify key project risks | High probability, medium impact | Conduct stakeholder interviews and risk workshops | Risk Officer (John Doe) | Week 1–2 | In Progress
2 | Assess technical feasibility risks | Medium probability, high impact | Review system design documentation and simulations | Engineering Team | Week 2–3 | Planned
3 | Identify supply chain disruptions | <Low probability, high impact | Establish alternate suppliers and inventory buffers | Sourcing Manager (Jane Smith) | Week 3–4 | Planned
4 | Review compliance and regulatory risks | High probability, medium impact | Update legal review checklist and training plans | Compliance Officer (Mike Johnson) | Week 4–5 | Pending Review
5 | Monitor and validate mitigation effectiveness | Medium probability, low impact | Weekly risk review meetings and audits | Risk Committee | Week 5–6 | Scheduled
6 | Update risk register and communicate findings | Low probability, low impact | Distribute updated report to stakeholders | Risk Officer (John Doe) | Week 6–7 | To Be Completed