## Worksheet
Date | Risk Identified | Likelihood (1–5) | Impact (1–5)> | Risk Score (Likelihood × Impact) | Mitigation Strategy | Owner | Status
2024-04-01 | Data breach due to unpatched systems | 4 | 5 | 20 | Implement automated patch management and conduct quarterly vulnerability scans. | IT Security Team | Active
2024-04-05 | Third-party vendor failure | 3 | 4 | 12 | Establish dual sourcing and SLA monitoring with backup vendors. | Operations Manager | Planned
2024-04-10 | Employee error leading to data misallocation | 2 | 3 | 6 | Conduct mandatory training and implement access review controls. | HR & Compliance | Ongoing
2024-04-15 | Outage due to server overload | 5 | 4 | 20 | Scale cloud infrastructure and add auto-scaling capabilities. | Cloud Architecture Team | High Priority