## Worksheet
Date | Risk Identified | Likelihood (1-5) | Impact (1-5) | Risk Score (Likelihood × Impact) | Mitigation Strategy | Owner | Status
2024-04-01 | Server downtime due to hardware failure | 3 | 4 | 12 | Implement redundant servers and regular maintenance checks | IT Department | In Progress
2024-04-02 | Data breach via unsecured third-party API | 5 | 5 | 25 | Restrict API access, implement encryption and audit logs | Security Team | Pending Action
2024-04-03 | Supply chain delay affecting delivery timelines | 2 | 3 | 6 | Establish backup suppliers and buffer inventory | Operations Manager | Completed
2024-04-04 | Employee non-compliance with access controls | 3 | 4 | 12 | Conduct mandatory security training and enforce role-based access | HR & Compliance | Planned