## Worksheet
Date | Risk Identified | Likelihood (1–5) | Impact (1–5) | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Person | Action Status
2024-04-01 | Data breach due to unpatched system | 4 | 5 | 30 | Implement patch management protocol and quarterly audits | IT Manager | In Progress
2024-04-05 | Third-party vendor failure | 3 | 4 | 12 | Diversify vendor base and include SLA reviews | Operations Director | Planned
2024-04-10 | Cyber attack via phishing | 5 | 5 | 25 | Enhance employee training and email filtering tools | Security Officer | Urgent Action Required
2024-04-15 | Regulatory non-compliance | 3 | 5 | 15 | Conduct compliance audit and update documentation | Legal Counsel | Scheduled
2024-04-20 | Power outage at data center | 4 | 4 | 16 | Install UPS and redundant power supply | Facilities Manager | Pending Approval