## Worksheet
Date | Risk Identified | Likelihood (1-5) | Impact (1-5) | Mitigation Strategy | Owner | Status
2024-04-01 | Network downtime due to hardware failure | 4 | 3 | Install redundant servers and daily backups | Alex Johnson | Planned
2024-04-05 | Insufficient cybersecurity awareness training | 3 | 5 | Conduct monthly security drills and provide training modules | Sarah Lee | Active
2024-04-10 | Data breach via unsecured third-party app | 5 | 4 | Implement strict vendor access controls and audit logs | David Chen | Urgent
2024-04-15 | Unplanned staff turnover in IT department | 2 | 4 | Develop internal succession plan and cross-train team members | Lisa Park | Scheduled