## Worksheet
Date | Risk Identified | Impact Level | Likelihood | Mitigation Strategy | Owner | Status (Planned/In Progress/Completed)
2024-04-01 | Data Breach Due to Unpatched Systems | High | Medium | Schedule patching within 7 days; implement automated monitoring. | IT Security Team | Planned
2024-04-05 | Third-Party Vendor Failure | Medium | High | Diversify vendor base; establish service level agreements with SLAs. | Operations Manager | In Progress
2024-04-10 | Regulatory Compliance Gap | High | Low | Conduct compliance audit; update policy documentation. | Legal & Compliance Officer | Planned
2024-04-15 | Cyberattack via Phishing | High | Medium | Enhance employee training; deploy advanced email filtering. | HR & Security Team | Completed