## Worksheet
Date | Risk Identified | Likelihood | Impact th> | Risk Rating (Likelihood × Impact) | Mitigation Strategy | Responsible Person | Action Status
2024-04-01 | Data breach due to outdated software | High | High | Very High (9) | Implement patch management and security audits | IT Manager | In Progress
2024-04-05 | Employee phishing vulnerability | Medium | High | High (6) | Conduct quarterly phishing simulations and training | Security Officer | Planned
2024-04-10 | Server downtime during maintenance | Low | Medium | Medium (3) | Schedule maintenance during off-peak hours | Network Admin | Completed
2024-04-15 | Insufficient access controls | High | Medium | High (6) | Enforce role-based access control (RBAC) | Compliance Officer | Pending Review