## Worksheet
Date | Risk Identified | Impact Level | Likelihood | Mitigation Action | Responsible Party | Completion Status
2024-04-01 | Data breach due to outdated software | High | Medium | Patch all vulnerable systems by end of month | IT Security Team | Pending
2024-04-05 | Vendor onboarding without compliance checks | Medium | High | Implement vendor compliance review checklist before engagement | Procurement Officer | Not Started
2024-04-10 | Server overload during peak hours | Low | High | Scale auto-scaling to handle traffic spikes | Cloud Operations Team | In Progress
2024-04-15 | Insufficient access controls for remote users | High | Medium | Enforce MFA and role-based access policies | Security Manager | Planned
2024-04-20 | Unapproved third-party API integrations | Medium | Medium | Approve all APIs through formal review process | DevOps Lead | Not Started