## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Current Control Measures | Risk Score (Likelihood × Impact) | Priority Level | Owner | Mitigation Strategy | Review Date
RISK-001 | Failure of critical server infrastructure | IT Operations | High | High | Redundant servers, backup systems in place | 9 (High) | Prioritized - Immediate Action Required | Jane Doe | Implement failover system and regular load testing | 2024-06-15
RISK-002 | Data breach due to unsecured endpoints | Security | Medium | High | Endpoint encryption, access controls enabled | 6 (Medium-High) | Prioritized - Action Needed in 30 days | John Smith | Deploy endpoint detection and response (EDR) tool | 2024-07-10
RISK-003 | Supply chain disruption due to vendor failure | <Operations | Medium | Medium | Bilateral contracts, alternative suppliers identified | 4 (Medium) | Moderate - Monitor and Review Quarterly | Lisa Chen | Strengthen vendor risk assessment process | 2024-08-01