## Worksheet
Risk Identifier | Risk Description | Likelihood | Impact | Current Controls | Risk Rating (Likelihood × Impact) | Ownership | Mitigation Plan | Next Review Date
RISK-001 | Data breach due to unsecured network access | High | Critical | Firewall, access controls, MFA | High (8/10) | IT Security Team | Implement network segmentation and weekly penetration testing | 2024-06-30
RISK-002 | Employee phishing susceptibility | Medium | High | Phishing simulation, training modules | Medium-High (6/10) | HR & Training Department | Conduct biannual phishing drills and update awareness campaigns | 2024-08-15
RISK-003 | System outage due to hardware failure | Low | Medium | Redundant servers, backup systems | Low (3/10) | Infrastructure Team | Replace aging hardware by Q4 2024 | 2024-12-01
RISK-004 | Compliance failure in data handling | High | Critical | Policy review, audits, documentation | High (9/10) | Legal & Compliance Office | Conduct quarterly compliance audits and update policies | 2024-05-31