## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Current Control Measures | Risk Rating (Likelihood × Impact) | Owner | Mitigation Strategy | Review Date
R-001 | Server outage due to hardware failure | Infrastructure | High | High | Redundant servers, daily backups | 9 (High) | IT Manager | Implement auto-failover and real-time monitoring | 2024-06-30
R-002 | Data breach through phishing attack | Security | Medium | High | Email filtering, security awareness training | 6 (Medium-High) | Security Officer | Enhance multi-factor authentication and phishing simulation | 2024-07-15
R-003 | Project scope creep leading to delays | Project Management | High | Medium | Change control process, stakeholder approvals | 6 (Medium-High) | Project Director | Introduce agile sprints and regular scope reviews | 2024-08-05
R-004 | Regulatory non-compliance due to policy gaps | Compliance | Medium | High | Monthly audits, compliance checklist updates | 6 (Medium-High) | Compliance Lead | Conduct annual compliance gap analysis and training | 2024-09-10