## Worksheet
Risk Identifier | Risk Description | Likelihood | Impact | Risk Rating | Mitigation Strategy | Responsible Party | Review Date
R-001 | Loss of customer data due to system breach | High | Critical | Severe (5/5) | Implement end-to-end encryption and regular audits | CISO | 2024-03-30
R-002 | Delayed product launch due to supply chain issues | Medium | High | High (4/5) | Diversify suppliers and establish backup plans | Supply Chain Manager | 2024-04-15
R-003 | Cyber attack on payment processing system | High | Critical | Severe (5/5) | Conduct penetration testing quarterly and update firewalls | IT Security Team | 2024-05-05
R-004 | Regulatory non-compliance due to outdated policies | Medium | High | High (4/5) | Conduct policy review and automate compliance checks | Legal & Compliance Officer | 2024-06-01