## Worksheet
Date | Risk Identifier | Risk Description | Probability | Impact th> | Risk Level | Owner | Mitigation Strategy | Status
2023-10-05 | RISK-001 | System outage due to server failure | High | Critical | Critical | IT Department | Implement redundant servers and regular failover testing | Active
2023-10-05 | RISK-002 | Data breach via phishing attack | Medium | High | High | Security Team | Conduct employee training and deploy advanced email filters | Pending Review
2023-10-05 | RISK-003 | Third-party vendor failure | Medium | Medium | Medium | Procurement Office | Identify alternate vendors and establish SLAs | In Progress
2023-10-05 | RISK-004 | Regulatory non-compliance | Low | High | High | Compliance Officer | Conduct quarterly audits and update policies | Planned