## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Current Status | Responsible Party | Mitigation Strategy | Due Date | Last Reviewed
RISK-001 | System outage due to server failure | Operational Risk | High | High | Active | IT Operations Team | Implement redundant servers and automatic failover | 2024-06-15 | 2024-03-10
RISK-002 | Data breach from unauthorized access | Security Risk | Medium | Critical | Pending Action | Security Administration | Enforce multi-factor authentication and regular audits | 2024-07-30 | 2024-03-15
RISK-003 | Supply chain delay affecting product delivery | Operational Risk | Low | Medium | Monitored | Logistics Department | Diversify suppliers and establish buffer stock | 2024-08-10 | 2024-03-20
RISK-004 | Compliance failure with regulatory updates | Legal Risk | High | High | Active | Compliance Officer | Conduct quarterly compliance reviews and training | 2024-09-05 | 2024-03-18