## Worksheet
Risk Identifier | Risk Description | Risk Category | Likelihood | Impact | Risk Rating (Likelihood × Impact) | Current Controls | Ownership | Mitigation Strategy | Review Date
RISK-001 | System outage due to server failure | Operational | High | High | High | Redundant servers in backup data center | IT Operations Team | Implement automated failover and monitoring alerts | 2024-06-30
RISK-002 | Data breach due to phishing attack | Security | Medium | Critical | High | Email filtering, user training, multi-factor authentication | Security Operations Team | Conduct quarterly phishing simulations and update policies | 2024-07-15
RISK-003 | Compliance violation due to outdated policies | Regulatory | Low | High | Medium | Annual policy review and audit process | Legal & Compliance Office | Update all policies in line with GDPR and SOX regulations | 2024-09-01