## Worksheet
Risk ID | Risk Description | Asset Affected | Likelihood | Impact | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Due Date | Status
RISK-001 | Cyberattack on customer data systems | Customer Database Server | High | Critical | 8 | Implement multi-factor authentication and encryption | IT Security Team | 2024-06-30 | Active
RISK-002 | Server outage due to power failure | Primary Data Center | Medium | High | 6 | Install backup generators and UPS systems | Facilities Management | 2024-07-15 | Pending Review
RISK-003 | Third-party vendor data breach | External Vendor Systems | High | Medium | 7 | Conduct vendor risk assessments and contract audits | Legal & Compliance Office | 2024-08-05 | Planned
RISK-004 | Regulatory non-compliance due to process errors | HR & Finance Departments | Medium | High | 5 | Train staff on compliance procedures and implement automated checks | HR & Compliance Manager | 2024-09-10 | In Progress