## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact(th) | Risk Score | Owner | Mitigation Plan | Status | Last Updated
RISK-001 | Loss of critical data due to cyberattack | Security | High | High | 9 | Jane Doe | Implement multi-factor authentication and regular backups. | Pending Review | 2024-03-15
RISK-002 | Supply chain disruption due to vendor failure | Operations | Medium | High | 7 | John Smith | Diversify suppliers and maintain safety stock. | In Progress | 2024-03-10
RISK-003 | System downtime during peak hours | IT Infrastructure | High | Medium | 8 | Alice Johnson | Upgrade server capacity and implement load balancing. | Planned | 2024-04-01
RISK-004 | Compliance breach due to policy violation | Legal & Compliance | Medium | High | 7 | Michael Brown | Pilot compliance training program and audit process. | Ongoing | 2024-03-05