## Worksheet
Risk Identifier | Risk Description | Likelihood | Impact | Risk Score (Likelihood × Impact) | Mitigation Strategy | Responsible Party | Review Date
RISK-001 | Data breach due to unpatched software systems. | High | Critical | 9 (9) | Implement automatic patch management and conduct quarterly security audits. | IT Security Team | 2024-06-15
RISK-002 | Supply chain disruption from key vendor failure. | Medium | High | 6 (6) | Diversify suppliers and establish backup vendors. | Procurement Manager | 2024-07-10
RISK-003 | System outage due to server failure. | High | Medium | 6 (6) | Deploy redundant servers and implement failover protocols. | System Operations Team | 2024-08-05
RISK-004 | Compliance violation due to incorrect documentation. | Low | High | 3 (3) | Introduce automated compliance reporting and training sessions. | Legal & Compliance Officer | 2024-09-12
RISK-005 | Employee error leading to financial loss. | Medium | Medium | 4 (4) | Conduct mandatory training and implement dual approvals for high-value transactions. | Finance Team | 2024-10-01