## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Current Status | Owner | Mitigation Strategy | Last Reviewed Date | Action Required
RISK-001 | Data breach due to unsecured third-party access | Security | High | Critical | Active | IT Security Lead | Implement multi-factor authentication (MFA) and access reviews. | 2024-03-15 | Enforce MFA rollout by Q3
RISK-002 | Supply chain disruption from vendor failure | Operations | Medium | High | Monitored | Procurement Manager | Identify backup vendors and diversify suppliers. | 2024-04-05 | Complete supplier audit by May 30
RISK-003 | Compliance failure with GDPR regulations | Regulatory | High | Critical | Pending Review | Legal Officer | Update data processing agreements and conduct staff training. | 2024-05-01 | Complete compliance review by June 30
RISK-004 | Cyberattack via phishing campaign | Security | High | High | Active | Cybersecurity Analyst | Deploy email filtering and user awareness training. | 2024-03-20 | Launch phishing simulation by April 15
RISK-005 | Key personnel departure affecting operations | Human Resources | Medium | Moderate | Active | HR Director | Document critical roles and implement succession planning. | 2024-03-30 | Finalize succession plan by May 10