## Worksheet
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Rating | Owner | Mitigation Strategy | Status | Last Updated
RISK-001 | System downtime due to server failure | IT Infrastructure | Moderate | High | Medium-High | Jane Smith | Backup servers with auto-switching protocol | Active | 2024-03-15
RISK-002 | Data breach through unsecured endpoints | Security | High | Very High | High | Robert Chen | Mandatory endpoint encryption and user access audits | Pending Review | 2024-03-10
RISK-003 | Compliance failure due to outdated policies | Regulatory | Low | High | Moderate | Sarah Patel | Policy review and automated compliance checks every 6 months | Planned | 2024-03-05
RISK-004 | Third-party vendor failure | External Dependencies | Moderate | Moderate | Moderate | Michael Davis | Dual sourcing and SLA monitoring with failover plans | Active | 2024-03-12