## Worksheet
Risk ID | Risk Description | Risk Category | Likelihood | Impact th> | Current Risk Rating | Risk Owner | Mitigation Strategy | Contingency Plan | Detection Method | Review Date | Status | Last Updated
R-001 | System outage due to hardware failure | Operational Risk | Moderate | High | High (H) | J. Smith | Replace servers with redundant units every 3 years | Switch to cloud backup during outages | Monitoring via UPS and server logs | 2024-06-15 | Active | 2024-05-23
R-002 | Data breach through unsecured third-party access | Security Risk | High | Very High | Severe (S) | L. Chen | Implement strict access controls and MFA for all third parties | Pause data sharing until security audit completes | Regular penetration testing and logs review | 2024-07-10 | Active | 2024-05-18
R-003 | Compliance failure due to outdated regulations | Regulatory Risk | Low | Moderate | Moderate (M) | T. Rivera | Quarterly compliance review with legal team | Engage external consultants for audit readiness | Automated compliance reporting tools | 2024-08-05 | Pending Review | 2024-05-10
R-004 | Supply chain disruption from single vendor dependency | Operational Risk | Moderate | High | High (H) | M. Gupta | Diversify suppliers with pre-approved alternatives | Establish emergency vendor agreement pool | Supplier performance scoring and audits | 2024-06-30 | Active | 2024-05-31